## Login Page
Section | Details
Project Name | BrowserStack
Module Name | login
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 12
Executed Test Cases | 12
Passed Test Cases | 12
Failed Test Cases
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 12 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 12out of 12covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
We can login with only the specified deafult users
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
Add for crating a new user

## Search
Section | Details
Project Name | BrowserStack
Module Name | Search Bar
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 3
Executed Test Cases | 3
Passed Test Cases | 1
Failed Test Cases | 2
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 1 | 34%
Failed | 2 | 66%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 2
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 2
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 3 out of 3covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Search is not working
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Search is not working | Medium | pending
7. Recommendations
Search Bar should work

## HomePage
Section | Details
Project Name | BrowserStack
Module Name | Homepage
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 3
Executed Test Cases | 3
Passed Test Cases | 3
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 3 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 3 out of 3covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Home page is working fine
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations

## Add to cart
Section | Details
Project Name | BrowserStack
Module Name | Add to cart
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 26
Executed Test Cases | 26
Passed Test Cases | 20
Failed Test Cases | 6
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 1
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 20 | 77%
Failed | 6 | 23%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 6
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 1
Low Severity Defects | 5
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 26 out of 26covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Add to cart is working fine and checkout process
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
No validation at while checkouting | Low | Pending
No description related to product | Medium | Pending
7. Recommendations
Add description to products

## RemoveFromCart
Section | Details
Project Name | BrowserStack
Module Name | Remove from Cart
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 4
Executed Test Cases | 4
Passed Test Cases | 4
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 4 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 4out of 4covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Femove from cart is working fine
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
Can add popup like item removed from cart

## Responsiveness
Section | Details
Project Name | BrowserStack
Module Name | Responsiveness
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 1
Executed Test Cases | 1
Passed Test Cases | 0
Failed Test Cases | 1
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | No
Manual Test Cases | 1
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 0 | 0%
Failed | 1 | 100%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 1 out of 1 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
No responsiveness across different devices
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
No responsiveness across different devices | Medium | Pending
7. Recommendations
Add Responsiveness

## Logout
Section | Details
Project Name | BrowserStack
Module Name | Logout
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 1
Executed Test Cases | 1
Passed Test Cases | 1
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 1 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 1 out of 1 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Logout link is working fine
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
Add a popup like logouted successfully

## Footer Links
Section | Details
Project Name | BrowserStack
Module Name | Footer Links
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 1
Executed Test Cases | 1
Passed Test Cases | 0
Failed Test Cases | 1
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 0 | 0%
Failed | 1 | 100%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 1 out of 1 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
No page related to privacy policy
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
No page related to privacy policy | Medium | Pending
7. Recommendations
Add some privacy policy details

## HeaderLinks
Section | Details
Project Name | BrowserStack
Module Name | Footer Links
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 3
Executed Test Cases | 3
Passed Test Cases | 3
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 3 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 3out of 3 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Header Links working fine
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations

## Subscribe letter
Section | Details
Project Name | BrowserStack
Module Name | Subscribe to news letter
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 3
Executed Test Cases | 3
Passed Test Cases | 2
Failed Test Cases | 1
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 2 | 67%
Failed | 1 | 33%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 3out of 3 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
No validation at subscribe email
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
f valid email and no email to subscription | Medium | Pending
7. Recommendations
Valid ation and subscription message

## Filters
Section | Details
Project Name | BrowserStack
Module Name | Filters
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | K.Jayadeep
Date
1. Test Summary
Metric | Count
Total Test Cases | 12
Executed Test Cases | 12
Passed Test Cases | 12
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 0
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 12 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 12out of 12 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Filters and vendors selection is working Fine
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
Add a filter option to dynamically adjust price and filter